## Sheet1
Date | Emp Id | Emp Name | Task Assigned | Status
19/09/25 | 6152782 | V Pratheek | Basic Frontend | Done
| 6152777 | Shriansh Kulkarni | Web Api design | Done
| 6152784 | Aditya V | Web Api design | Done
| 6152779 | Rohan K | Database design | Done
| 6152794 | Saili P | Database design | Done
22/09/25 | 6152782 | V Pratheek | Building Web Api | Done
| 6152777 | Shriansh Kulkarni | Web Api Contollers | Done
| 6152784 | Aditya V | Models and Entities | Done
| 6152779 | Rohan K | Models and Entities | Done
| 6152794 | Saili P | Frontend Login and redirection | Done
23/09/25 | 6152782 | V Pratheek | Services | Done
| 6152777 | Shriansh Kulkarni | Services | Done
| 6152784 | Aditya V | Frontend Designing | Done
| 6152779 | Rohan K | DTO's | Done
| 6152794 | Saili P | DTO's | Done
24/09/2025 | 6152782 | V Pratheek | Integrate login API with frontend and test redirection | Done
| 6152777 | Shriansh Kulkarni | Task Upload page in Trainer and styling | Done
| 6152784 | Aditya V | Test file upload UI and error messages | Done
| 6152779 | Rohan K | Design dashboard layout for Intern view | Done
| 6152794 | Saili P | Design dashboard layout for Trainer view | Done
25/09/2025 | 6152782 | V Pratheek | Implement role-based routing logic for Intern and Trainer | Done
| 6152777 | Shriansh Kulkarni | Fix routing issues in Trainer dashboard | Done
| 6152784 | Aditya V | Test frontend-backend integration for Quiz section | Done
| 6152779 | Rohan K | Create reusable dashboard components for different user roles | Done
| 6152794 | Saili P | Review and clean up unused backend endpoints | Done
26/09/2025 | 6152782 | V Pratheek | Setup authentication service and token handling | Done
| 6152777 | Shriansh Kulkarni | Validate uploaded file content before processing | Done
| 6152784 | Aditya V | Add support for CSV and Excel formats in Quiz module | Done
| 6152779 | Rohan K | Create reusable dashboard components for different user roles | Done
| 6152794 | Saili P | Document supported file formats and upload instructions | Done
29/09/2025 | 6152782 | V Pratheek | Setup backend logic for leaderboard data | Done
| 6152777 | Shriansh Kulkarni | Style Task Upload section and test it | Done
| 6152784 | Aditya V | Design Quiz Upload section and test it | Done
| 6152779 | Rohan K | Add dropdown for Task and Quiz Score in Trainer view | Done
| 6152794 | Saili P | Create API for analytics graphs | Done
30/09/2025 | 6152782 | V Pratheek | Role based Access login Fixes and Testing | Done
| 6152777 | Shriansh Kulkarni | Task Upload logic and Implementation | Done
| 6152784 | Aditya V | Quiz Upload logic and implementation | Done
| 6152779 | Rohan K | User CURD Operations testing according to Token Validation | Done
| 6152794 | Saili P | Logic Design for Leaderboard Section in the Manager | Done
30/09/2025 | 6152782 | V Pratheek | Password hashing Implementation | Done
| 6152777 | Shriansh Kulkarni | Task Management in the Trainer Section | Done
| 6152784 | Aditya V | Quiz Management in the Trainer Section | Done
| 6152779 | Rohan K | User section Management and Testing | Done
| 6152794 | Saili P | Implementation of Leaderboard Section of Trainer | Done
2025-01-10 | 6152782 | V Pratheek | Logic Design for Scoring Submissions | Done
| 6152777 | Shriansh Kulkarni | Task Management in the Intern Section | Done
| 6152784 | Aditya V | Quiz Management int the Intern Section | Done
| 6152779 | Rohan K | Dashborad Routing and its Bug Fixes | Done
| 6152794 | Saili P | Implementation of Leaderboard Section of Intern | Done
2025-03-10 | 6152782 | V Pratheek | Testing for Integration of JWT and Passsword Hashing | Done
| 6152777 | Shriansh Kulkarni | Task Assigning to Interns after Task Upload | Done
| 6152784 | Aditya V | Quiz Assigning to Interns after parsing | Done
| 6152779 | Rohan K | Input Validation , Field Validation and Testing | Done
| 6152794 | Saili P | Implementation of Analytics Section of Trainer | Done
2025-04-10 | 6152782 | V Pratheek | Logic for the Radar Graph in Trainer | Done
| 6152777 | Shriansh Kulkarni | Intern Task Submission section | Done
| 6152784 | Aditya V | Intern Quiz Submission section | Done
| 6152779 | Rohan K | Test file upload UI and error messages | Done
| 6152794 | Saili P | Implementation of Analytics Section of Manager/Trainer | Done
2025-05-10 | 6152782 | V Pratheek | Implementation of Score Submissions of task | Done
| 6152777 | Shriansh Kulkarni | Intern Task Submission Logic and Implemenation | Done
| 6152784 | Aditya V | Intern Quiz Submission Logic and Implementation | Done
| 6152779 | Rohan K | Randomization of the Quiz Questions | Done
| 6152794 | Saili P | Dynamic Score Aggregation of Interns | Done
2025-06-10 | 6152782 | V Pratheek | Documentation Completion of Project | Done
| 6152777 | Shriansh Kulkarni | Soft Deletion of Task in Trainer and Intern | Done
| 6152784 | Aditya V | Automatic Grading logic for Quiz and its Implementation | Done
| 6152779 | Rohan K | Power point Presentation of the Project | Done
| 6152794 | Saili P | Individual performance Analytics | Done